## Projects
ProjectID | ProjectName | Portfolio | Priority | Status | StartDate | EndDate | BudgetMillions | Project Manager
P001 | Substation Upgrade North | Transmission | High | Active | 2025-01-01 | 2025-09-30 | 12 | David Chen
P002 | Transmission Line Expansion | Transmission | High | Active | 2025-02-01 | 2025-12-31 | 25 | Jennifer Park
P003 | Dam Turbine Modernization | Generation | High | Planned | 2025-04-01 | 2026-03-31 | 40 | David Chen
P004 | Smart Meter Deployment | Distribution | Medium | Active | 2025-01-01 | 2025-07-31 | 8 | Jennifer Park
P005 | Grid Reliability Program | Distribution | High | Active | 2025-03-01 | 2025-12-31 | 15 | David Chen
P006 | Station Maintenance Upgrade | Transmission | Medium | Planned | 2025-06-01 | 2025-11-30 | 6 | Jennifer Park
P007 | Hydro Facility Inspection | Generation | Low | Active | 2025-01-01 | 2025-05-31 | 2 | David Chen
P008 | Substation Automation | Transmission | Medium | Planned | 2025-07-01 | 2026-02-28 | 10 | Jennifer Park
P009 | Vegetation Management | Distribution | Medium | Active | 2025-02-01 | 2025-10-31 | 5 | David Chen
P010 | Renewable Integration Study | Generation | High | Planned | 2025-05-01 | 2025-12-31 | 4 | Jennifer Park
P011 | Substation Refurbishment East | Transmission | High | Active | 2025-01-01 | 2025-12-31 | 18 | David Chen
P012 | Distribution Feeder Upgrade | Distribution | Medium | Active | 2025-03-01 | 2025-11-30 | 9 | Jennifer Park
P013 | Hydro Plant Asset Renewal | Generation | High | Planned | 2025-06-01 | 2026-06-30 | 35 | David Chen
P014 | Protection System Upgrade | Transmission | Medium | Active | 2025-02-01 | 2025-09-30 | 7 | Jennifer Park
P015 | Grid Modernization Initiative | Distribution | High | Active | 2025-01-01 | 2026-01-31 | 28 | David Chen
P016 | Dam Safety Program | Generation | High | Active | 2025-04-01 | 2026-03-31 | 22 | Jennifer Park
P017 | Distribution Automation | Distribution | Medium | Planned | 2025-05-01 | 2025-12-31 | 12 | David Chen
P018 | Transmission Capacity Expansion | Transmission | High | Planned | 2025-07-01 | 2026-07-31 | 32 | Jennifer Park
P019 | Environmental Compliance Upgrade | Generation | Low | Active | 2025-02-01 | 2025-08-31 | 4 | David Chen
P020 | Network Resiliency Program | Distribution | High | Active | 2025-01-01 | 2025-12-31 | 20 | Jennifer Park

## Resources
ResourceID | EmployeeName | Role | Department | MonthlyCapacity | AvailabilityFactor | EffectiveCapacity
R001 | Sarah Wong | Electrical Engineer | Engineering | 160 | 0.85 | 136
R002 | James Smith | Electrical Engineer | Engineering | 160 | 0.85 | 136
R003 | Mark Lee | Civil Engineer | Engineering | 160 | 0.9 | 144
R004 | Emily Brown | Civil Engineer | Engineering | 160 | 0.9 | 144
R005 | David Chen | Project Manager | PMO | 160 | 0.9 | 144
R006 | Jennifer Park | Project Manager | PMO | 160 | 0.9 | 144
R007 | Michael Johnson | Planner | Planning | 160 | 0.95 | 152
R008 | Karen Wilson | Planner | Planning | 160 | 0.95 | 152
R009 | Alex Garcia | Business Analyst | Analytics | 160 | 0.95 | 152
R010 | Rachel Taylor | Business Analyst | Analytics | 160 | 0.95 | 152
R011 | Robert Evans | Electrical Engineer | Engineering | 160 | 0.85 | 136
R012 | Linda Martin | Electrical Engineer | Engineering | 160 | 0.85 | 136
R013 | Chris White | Civil Engineer | Engineering | 160 | 0.9 | 144
R014 | Daniel Harris | Civil Engineer | Engineering | 160 | 0.9 | 144
R015 | Susan Moore | Planner | Planning | 160 | 0.95 | 152
R016 | Kevin Young | Planner | Planning | 160 | 0.95 | 152
R017 | Lisa Walker | Business Analyst | Analytics | 160 | 0.95 | 152
R018 | Andrew Hall | Business Analyst | Analytics | 160 | 0.95 | 152
R019 | Brian King | Project Manager | PMO | 160 | 0.9 | 144
R020 | Nancy Scott | Project Manager | PMO | 160 | 0.9 | 144

## Resource Demand
ProjectID | Role | Month | HoursRequired
P001 | Electrical Engineer | 2026-01-25 | 220
P001 | Electrical Engineer | 2026-02-25 | 240
P001 | Project Manager | 2026-01-25 | 80
P001 | Project Manager | 2026-02-25 | 80
P002 | Electrical Engineer | 2026-02-25 | 260
P002 | Electrical Engineer | 2026-03-25 | 280
P002 | Project Manager | 2026-02-25 | 100
P003 | Civil Engineer | 2026-04-25 | 220
P003 | Civil Engineer | 2026-05-25 | 240
P004 | Business Analyst | 2026-01-25 | 120
P004 | Business Analyst | 2026-02-25 | 120
P005 | Planner | 2026-03-25 | 180
P005 | Planner | 2026-04-25 | 200
P006 | Electrical Engineer | 2026-06-25 | 180
P007 | Civil Engineer | 2026-01-25 | 80
P008 | Electrical Engineer | 2026-07-25 | 220
P009 | Planner | 2026-02-25 | 140
P010 | Business Analyst | 2026-05-25 | 100
P011 | Electrical Engineer | 2026-01-25 | 220
P011 | Electrical Engineer | 2026-02-25 | 240
P011 | Project Manager | 2026-01-25 | 80
P011 | Planner | 2026-01-25 | 60
P012 | Planner | 2026-03-25 | 180
P012 | Planner | 2026-04-25 | 200
P012 | Project Manager | 2026-03-25 | 80
P012 | Business Analyst | 2026-04-25 | 100
P012 | Planner | 2026-03-25 | 180
P012 | Planner | 2026-04-25 | 200
P012 | Project Manager | 2026-03-25 | 80
P012 | Business Analyst | 2026-04-25 | 100
P001 | Electrical Engineer | 2026-07-25 | 260
P001 | Electrical Engineer | 2026-08-25 | 280
P002 | Electrical Engineer | 2026-07-25 | 300
P002 | Electrical Engineer | 2026-08-25 | 320
P003 | Civil Engineer | 2026-07-25 | 260
P003 | Civil Engineer | 2026-08-25 | 280
P004 | Business Analyst | 2026-06-25 | 120
P004 | Business Analyst | 2026-07-25 | 140
P005 | Planner | 2026-07-25 | 220
P005 | Planner | 2026-08-25 | 240
P006 | Electrical Engineer | 2026-07-25 | 200
P007 | Civil Engineer | 2026-07-25 | 100
P008 | Electrical Engineer | 2026-08-25 | 240
P009 | Planner | 2026-08-25 | 180
P010 | Business Analyst | 2026-07-25 | 100
P001 | Electrical Engineer | 2026-07-25 | 260
P001 | Electrical Engineer | 2026-08-25 | 280
P002 | Electrical Engineer | 2026-07-25 | 300
P002 | Electrical Engineer | 2026-08-25 | 320
P003 | Civil Engineer | 2026-07-25 | 260
P003 | Civil Engineer | 2026-08-25 | 280
P004 | Business Analyst | 2026-06-25 | 120
P004 | Business Analyst | 2026-07-25 | 140
P005 | Planner | 2026-07-25 | 220
P005 | Planner | 2026-08-25 | 240
P006 | Electrical Engineer | 2026-07-25 | 200
P007 | Civil Engineer | 2026-07-25 | 100
P008 | Electrical Engineer | 2026-08-25 | 240
P009 | Planner | 2026-08-25 | 180
P010 | Business Analyst | 2026-07-25 | 100